## Task Allocation
Task ID | Workstream | Task / Deliverable | Frontend Tasks | Backend / AI / Edge Tasks | Integration / QA Tasks | Priority | Dependencies / Inputs | Proposed Owner Allocation | Acceptance / Done Criteria | Status | Planned Start | Planned Finish | Actual Finish | Remarks
T001 | Project & Governance | Confirm final POC scope, locations (Ahmedabad and Bhubaneswar), 7-day POC dates, and demo schedule | Display agreed scope, locations and timeline in POC overview | Confirm API contract, deployment architecture, supported use cases and schedule | Project lead to sign off scope and acceptance matrix | P0 | Customer confirmation | Project Manager / Customer SPOC | Approved scope and dated plan recorded | Not Started
T002 | Project & Governance | NDA, confidentiality, client secrecy and company-only representation | Ensure no client-sensitive information is exposed in screens or demo materials | Access controls, secret management, data retention and approved branding/configuration | Review logs, screenshots, exports and demo material for confidential data | P0 | NDA and customer branding guidance | Project Manager + Security/DevOps | NDA obligations documented; only approved company identity used | Not Started
T003 | Hardware & Edge | Receive and inventory Jetson Orin Nano 16GB hardware and accessories | Show device inventory/status in setup checklist if dashboard exists | Verify carrier, M.2/SSD, Gigabit Ethernet, power supply, enclosure and JetPack/Linux compatibility | Record serials, accessories and physical condition | P0 | Hardware expected Wednesday/Thursday; exact date to confirm | Hardware/Edge Engineer | Hardware checklist completed | Not Started
T004 | Hardware & Edge | Install Ubuntu Server 24.04 / compatible JetPack image and drivers | Optional device setup/status page | Validate actual OS, JetPack, CUDA/TensorRT and camera SDK compatibility; resolve version conflicts | Run boot, storage, thermal, power and network tests | P0 | T003; confirm Ubuntu 24.04 support for selected JetPack | Edge/DevOps Engineer | Documented supported software stack; all smoke tests pass | Not Started
T005 | Hardware & Edge | Configure edge AI runtime and service supervision | Show runtime/engine health and service status | Container/service setup, model loading, restart policy, logs, resource monitoring and watchdog | Power-cycle and service-recovery test | P0 | T004 | Edge AI Engineer + DevOps | Services start on boot and recover after failure | Not Started
T006 | Camera & Stream | Camera discovery, stream ingest and camera configuration | Camera list with camera ID, name, location, stream state and last frame time | RTSP/ONVIF or agreed stream integration, reconnect logic, codec/resolution/FPS configuration | Test each camera feed and reconnect after stream interruption | P0 | Camera models, credentials and streams available | Video Integration Engineer + Frontend Developer | All agreed camera streams are ingested and status is visible | Not Started
T007 | Camera & Stream | Multi-camera processing capacity and resource profiling | Display per-camera processing state and FPS if available | Benchmark decode, inference, memory, CPU/GPU, temperature and throughput for all required streams | Run sustained test and record supported camera count and limitations | P0 | T006; agreed camera count/resolution/FPS | Edge AI Engineer + QA | Measured capacity documented; no unsupported capacity claims | Not Started
T008 | ANPR / ALPR | Vehicle and number-plate detection/OCR | ANPR event list with plate text, timestamp, camera, confidence and snapshot | Detection/OCR pipeline, confidence thresholds, plate crop/full frame, event IDs and deduplication | Test day/night, angles, motion, blur and plate variations | P0 | T006; representative test footage | AI/Computer Vision Engineer + Frontend Developer | Events and images displayed; test results recorded against agreed criteria | Not Started
T009 | ANPR / ALPR | Stolen/blacklisted vehicle matching and alert | Blacklist status, match result and alert detail view | Watchlist ingestion/update, normalized plate matching, audit trail and alert rules | Test match, non-match, duplicate and stale-list cases | P0 | T008; authorized test list/API | Backend Engineer + AI Engineer | Approved test entries trigger correct alerts | Not Started
T010 | ANPR / ALPR | Push ANPR events to customer-provided API | Delivery state, event detail and retry/error indicator if UI is included | API client, authentication, schema mapping, image/video references, camera metadata, timestamp, retries and idempotency | Contract test with customer endpoint; validate payload and delivery logs | P0 | Customer API docs, credentials, network access | Backend/API Engineer | Customer confirms valid payloads and receipt | Not Started
T011 | FRS | Face detection and multi-face tracking per frame | Face event list, bounding boxes/face crops where authorized, timestamp and camera | Face detection/tracking pipeline; benchmark multi-face behavior and edge resource use | Test multiple faces, occlusion, crowd density and tracking continuity | P0 | T006; approved test dataset and lawful basis | AI/Computer Vision Engineer + Frontend Developer | Behavior demonstrated and limitations documented | Not Started
T012 | FRS | Watchlist matching for missing persons / wanted persons | Match review screen with confidence, case/reference ID and human review action | Watchlist ingestion, feature matching, thresholds, versioning, access restrictions and audit logs | Use authorized test identities; verify match/non-match and false alerts | P0 | Authorized watchlist, API/spec, customer approval | AI Engineer + Backend Engineer | Human-reviewed test matches logged; no unauthorized live watchlist use | Not Started
T013 | FRS | 1:1 face verification and liveness / anti-spoofing | Verification result and operator review state | 1:1 matching, liveness capability assessment, threshold config and audit events | Test genuine and approved spoof test cases; record limitations | P1 | Supported model/device capabilities and approved test data | AI Engineer + Backend Engineer | Only capabilities validated on supplied hardware are represented | Not Started
T014 | FRS | Push facial events to customer API with image/video footprint and camera details | Event detail with delivery status | Payload mapping, protected media references, authentication, retry and audit logging | Validate schema, access permissions and end-to-end delivery | P0 | Customer API docs; privacy/security approval | Backend/API Engineer | Customer validates event and media reference delivery | Not Started
T015 | Weapon Detection | Weapon detection model and alert rules | Weapon event list, snapshot, camera, time, confidence and operator status | Model inference, supported weapon classes, confidence thresholds, event deduplication | Test using approved footage/staged safe scenarios; tune false positives | P0 | Approved sample footage and defined weapon classes | AI/Computer Vision Engineer + Frontend Developer | Agreed test cases documented with measured results | Not Started
T016 | Weapon Detection | Push weapon events to customer API | API delivery state and event detail | Event schema, media reference, camera metadata, authentication, retry and idempotency | Customer endpoint contract test and receipt confirmation | P0 | Customer API docs and endpoint availability | Backend/API Engineer | Customer confirms successful event receipt | Not Started
T017 | Fire & Smoke | Fire and smoke detection | Fire/smoke event list and alert severity | Inference pipeline, supported classes, confidence threshold, event cooldown | Test approved sample footage and false-positive scenarios | P0 | Approved footage and model availability | AI/Computer Vision Engineer + Frontend Developer | Results measured against agreed scenarios | Not Started
T018 | Crowd & Object Analytics | Person/vehicle/object multi-class detection | Live overlay or event list with object class and confidence | Model inference, class mapping, track IDs and event generation | Test representative scenes and supported classes | P0 | T006; agreed object classes | AI/Computer Vision Engineer + Frontend Developer | Required classes shown and logged | Not Started
T019 | Crowd & Object Analytics | People counting, crowd density and heat map | Counts, density view and heat map visualization | Tracking/counting logic, zones, aggregation windows and calibration | Compare counts against manually labelled test clips | P1 | Camera view/scene calibration and test footage | AI Engineer + Frontend Developer | Count accuracy and limitations documented | Not Started
T020 | API & Event Platform | Common event schema and event persistence | Unified event table with filters by use case, camera, time and status | Canonical schema, database, event IDs, timestamps/timezone, media metadata and retention | Schema validation, duplicate handling and data consistency tests | P0 | Event fields agreed with customer | Backend/API Engineer + Frontend Developer | All use cases use a consistent, validated event structure | Not Started
T021 | API & Event Platform | Live event push reliability and delivery tracking | Delivery status, retry count and last error (role-restricted) | Queue/outbox, retry/backoff, idempotency, timeouts, dead-letter handling and monitoring | Simulate endpoint downtime, timeout and recovery | P0 | Customer API accessible; authentication details supplied | Backend/API Engineer + DevOps | Recovery and duplicate prevention verified | Not Started
T022 | Central Dashboard | Central monitoring dashboard for POC | Overview cards, camera status, live events, filters, event detail and alert acknowledgement | Dashboard APIs, pagination, filtering, role-based data access and aggregation | Verify live refresh, empty/error/loading states and responsive layout | P0 | Approved UI expectations and backend event endpoints | Frontend Developer + Backend Engineer | Operators can view and review all agreed POC events | Not Started
T023 | Central Dashboard | Live stream and recorded-footage demonstration | Live view, playback control and event-to-video navigation where supported | Stream relay/playback integration, clip retrieval, timestamps and storage references | Verify playback access and event timestamp alignment | P1 | Recording source, storage and customer platform interfaces | Frontend Developer + Video Integration Engineer | Live/playback paths demonstrated where supplied systems support them | Not Started
T024 | Central ICCC Integration | Integrate with existing ICCC platform | Show incoming event/status in the agreed ICCC screen or agreed integration view | ICCC API/event contract, auth, mapping, acknowledgement and network configuration | End-to-end integration test with ICCC team | P0 | ICCC documentation, access, test environment and SPOC | Integration Engineer + Backend/API Engineer | Customer/ICCC team confirms events appear as agreed | Not Started
T025 | Security & Privacy | Secure API credentials, role access and audit logs | Login/roles; mask sensitive fields where required; authorized audit view | TLS, secrets storage, least privilege, access control, audit logging and retention settings | Security review and negative access tests | P0 | Customer security policy and NDA requirements | DevOps/Security Engineer + Backend Engineer | No secrets in code/logs; access tests pass | Not Started
T026 | Operations | Connectivity and offline buffering | Connection status and last successful sync indicator | 4G/5G router/SIM configuration, bandwidth measurement, reconnect and local queue/store-and-forward | Test weak signal, outage, recovery and queued event delivery | P0 | SIM/APN, coverage and customer network access | Network/Edge Engineer + Backend Engineer | Events recover/sync after connectivity restoration within agreed limits | Not Started
T027 | Operations | Time synchronization and event/video correlation | Consistent timestamps in event list and video playback | NTP/timezone configuration, timestamp normalization and clock drift monitoring | Compare edge, camera, API and ICCC timestamps | P0 | Network access to approved time source | DevOps + Video Integration Engineer | Timestamp drift is within agreed tolerance | Not Started
T028 | Performance & QA | Measure latency, accuracy, FPS and resource utilization | POC report/dashboard with measured metrics | Instrument capture-to-detection, detection-to-API latency, FPS, memory/GPU and temperature | Run repeatable tests; define denominator and ground-truth methodology | P0 | Acceptance thresholds and test plan approved | QA Lead + AI Engineer + Edge Engineer | Report contains measured values, test conditions and known limitations | Not Started
T029 | Performance & QA | Create use-case-specific POC acceptance matrix | Show test progress and pass/fail by use case if dashboard supports it | Define measurable criteria per use case: precision/recall or agreed accuracy, latency, delivery and stability | Jointly approve test cases, sample sizes and scoring method | P0 | Customer and project lead approval | QA Lead + Project Manager + Customer SPOC | Acceptance criteria signed off before formal POC | Not Started
T030 | Installation & Vehicle | Install, fabricate, mount and power edge hardware/cameras | Show installation checklist and device mapping if applicable | Vehicle mounting, vibration/thermal considerations, power conditioning, cable routing and safe installation | Physical inspection, ignition/power-cycle and road-test checks | P0 | Vehicle access, mount design and hardware arrival | Field/Hardware Engineer + Vehicle Installer | Installation is secure and passes power/operational checks | Not Started
T031 | Demonstration | Prepare live vehicle demonstration in Ahmedabad | Demo screen, use-case sequence and event evidence | Preload approved footage/test lists; verify all pipelines and API delivery | Rehearsal and demo checklist | P0 | Vehicle readiness, customer date and site access | Project Manager + Demo Lead + AI/Integration Team | Demonstration completed with evidence and issues logged | Not Started
T032 | Demonstration | Prepare live vehicle demonstration in Bhubaneswar, Odisha | Same approved dashboard and presentation with location-specific configuration | Validate connectivity, API route, camera setup and configuration at location | Rehearsal and site checklist | P0 | Travel/site access, connectivity and customer date | Project Manager + Field Engineer + Integration Team | Demonstration completed with evidence and issues logged | Not Started
T033 | POC Execution | Execute 7-day ground POC and daily review | Daily status, event review and issue tracker | Monitor uptime, event delivery, model behavior, edge health and API/ICCC integration | Daily report, defect triage, retest and evidence capture | P0 | Successful demo; agreed POC dates and acceptance matrix | POC Lead + QA Lead + All Workstream Owners | Daily logs complete; all deviations tracked | Not Started
T034 | Documentation & Handover | Prepare final POC report for Commissioner of Police | Presentation of validated results, sample events and limitations | Compile metrics, architecture, supported configurations, integration results and open risks | Customer review and approval of final report | P0 | T028-T033 results | Project Manager + QA Lead + Solution Architect | Evidence-backed report approved for submission | Not Started
T035 | Customisation | Evaluate only in-scope customisation requests during POC | Document requested UI changes and agreed priority | Assess impact on model/API/edge/integration, effort and feasibility | Log approve/defer/reject decision; avoid unapproved scope creep | P1 | Request from customer and scope approval | Project Manager + Relevant Technical Owner | Each request has owner, decision and acceptance note | Not Started
T036 | Release & Support | Package deployment, diagnostics and rollback | Build/version and health summary if UI supports it | Versioned deployment, config backup, logs, restart/rollback steps and known issues | Fresh-install test and handover walkthrough | P1 | Stable POC build | DevOps/Edge Engineer + QA Lead | Reproducible deployment and recovery instructions delivered | Not Started

## Role Allocation
Role / Allocation Pool | Responsibilities
Project Manager / POC Lead | Own scope, schedule, risks, customer coordination, daily review and final submission
Solution Architect | Own system architecture, interface definitions and technical decisions
Frontend Developer | Dashboard, event lists, camera views, filters, statuses and operator review screens
Backend / API Engineer | Event schema, APIs, persistence, retries, auth, audit and ICCC/customer API integration
AI / Computer Vision Engineer | ANPR, FRS, weapon, fire/smoke, crowd/object models, tuning and model benchmarks
Edge AI Engineer | Jetson deployment, model runtime, TensorRT/CUDA compatibility, resource profiling and recovery
Video Integration Engineer | RTSP/ONVIF, decoding, stream stability, playback and timestamp/video correlation
DevOps / Security Engineer | OS/runtime, networking, secrets, TLS, logs, monitoring, deployment and rollback
Hardware / Field Engineer | Device inventory, enclosure, power, vehicle installation, fabrication and physical testing
Network Engineer | 4G/5G connectivity, SIM/APN, bandwidth, reconnect and offline recovery
QA Lead | Test plans, ground truth, acceptance criteria, test evidence, regression and POC reporting
Customer / ICCC SPOC | Supply API specs/access, confirm requirements, validate events and sign off acceptance

## Milestones
Milestone ID | Milestone | Target / Timing | Proposed Owner | Status
M1 | Scope and acceptance criteria approved | Before build/demo | Project Manager + Customer SPOC | Pending
M2 | Jetson hardware received and compatibility verified | After hardware arrival (expected Wednesday/Thursday; confirm exact date) | Hardware/Edge Engineer | Pending
M3 | Camera streams and core AI pipelines working locally | Before vehicle demonstration | Video Integration + AI/Edge Engineers | Pending
M4 | Customer API and event schema tested | Before vehicle demonstration | Backend/API Engineer + Customer SPOC | Pending
M5 | Ahmedabad vehicle demonstration | Date/time to be confirmed | Project Manager + Demo Team | Pending
M6 | Bhubaneswar, Odisha demonstration | Date/time to be confirmed | Project Manager + Field/Integration Team | Pending
M7 | 7-day ground POC | After demo and joint approval | POC Lead + QA Lead + Workstream Owners | Pending
M8 | Final evidence-backed report for CP Sir | After 7-day POC | Project Manager + QA Lead | Pending

## Risks & Dependencies
Risk ID | Risk / Open Point | Severity | Mitigation / Action | Owner
R1 | Jetson Orin Nano 16GB / Ubuntu Server 24.04 / JetPack compatibility | High | Confirm supported JetPack, OS image, CUDA/TensorRT and model runtime before committing to full-stack performance. | Edge AI Engineer
R2 | All six use cases on one edge device | High | Benchmark streams and use cases together; agree camera count, resolution, FPS and concurrent inference scope. | Solution Architect + Edge AI Engineer
R3 | Customer API/ICCC interfaces not yet specified | High | Obtain API docs, schemas, authentication, media transfer rules, test endpoints and ICCC SPOC. | Backend/API Engineer + Customer SPOC
R4 | FRS watchlists and personal data | High | Use only authorized data; confirm legal basis, access controls, retention, audit and human-review process. | Customer SPOC + Security/Privacy Owner
R5 | 4G/5G bandwidth and field coverage | Medium | Measure throughput and latency at each site; define offline buffering and acceptable sync delay. | Network Engineer
R6 | Accuracy acceptance criteria not defined numerically | High | Jointly define test set, ground truth, precision/recall or other metric, sample size and pass thresholds per use case. | QA Lead + Customer SPOC
R7 | Live/recorded footage access and storage unclear | Medium | Confirm where recordings reside, how clips are retrieved, retention and secure media references. | Video Integration + Customer SPOC
R8 | Customisation may expand POC scope | Medium | Use change log and approve only customisation directly related to listed use cases. | Project Manager
R9 | Vehicle power, heat and vibration | Medium | Validate power budget, thermal limits, mounting, enclosure and recovery under vehicle conditions. | Hardware/Field Engineer

## Software Task Breakdown
Task ID | Email Scope / Use Case | Detailed Software Task (Email Scope Only) | Frontend Responsibility | Backend / AI / Edge Software Responsibility | API / ICCC Responsibility | Proposed Owner Role | Dependency / Input from Customer | Completion / POC Validation | Priority | Status | Planned Start | Planned Finish | Remarks
S01 | ANPR / ALPR | Number plate detection and OCR | Display detected number plate, captured image, camera details and event information for review. | Run number plate detection and OCR on the supplied camera stream using the agreed AI software. | No separate API change beyond sending the ANPR event as described in S03. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and representative test footage. | Demonstrate detection and OCR during POC; record observed results. | P0 | Not Started
S02 | ANPR / ALPR | Stolen / blacklisted vehicle alerts | Display the plate match result and corresponding alert. | Compare detected plate details with the customer-provided stolen/blacklisted vehicle data or interface, as agreed. | Send the related ANPR alert through the customer-provided API. | AI/Computer Vision Engineer; Backend/API Engineer; Frontend Developer | Authorized test list and matching rules/data from customer. | Demonstrate agreed test matches and non-matches; validate alert visibility. | P0 | Not Started
S03 | ANPR / ALPR | Push all ANPR events to customer-provided API in real time | Show event information and delivery result where the POC UI provides it. | Prepare ANPR event data and associated evidence references. | Push event to customer-provided API in real time with image, video footprint/reference and camera details. | Backend/API Engineer | Customer API documentation, endpoint, credentials and required payload format. | Customer endpoint receives and validates the ANPR event and associated fields. | P0 | Not Started
S04 | FRS | Face detection and multi-face tracking per frame | Display facial events and related image/camera information for operator review. | Process the camera stream for face detection and multi-face tracking per frame as specified. | No additional API scope beyond facial event push in S07. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and approved test footage/data. | Demonstrate face detection and multi-face tracking in agreed POC scenarios. | P0 | Not Started
S05 | FRS | Watchlist matching for missing persons / wanted criminals | Display potential watchlist match for human-in-the-loop validation. | Match detected faces against the customer-authorized watchlist using agreed software capabilities. | Include match event in the facial event API push in S07. | AI/Computer Vision Engineer; Backend/API Engineer; Frontend Developer | Authorized watchlist, approved test data and matching requirements. | Demonstrate agreed test cases with human review; record observed results. | P0 | Not Started
S06 | FRS | 1:1 verification, anti-spoofing/liveness and audit logging | Provide the verification result and human review/audit information required for the stated POC. | Implement 1:1 verification, liveness/anti-spoofing and audit logging to the extent supported by the agreed software and supplied edge hardware. | Facial events are transmitted under S07. | AI/Computer Vision Engineer; Backend/API Engineer; Frontend Developer | Approved test data and agreed verification/liveness scenarios. | Demonstrate the specified functions and audit records; document any capability limitations for the POC. | P0 | Not Started
S07 | FRS | Push all facial events to customer-provided API in real time | Show facial event and delivery result where the POC UI provides it. | Prepare facial event data and associated evidence references. | Push facial events to customer-provided API in real time with image, video footprint/reference and camera details. | Backend/API Engineer | Customer API documentation, endpoint, credentials and required payload format. | Customer endpoint receives and validates facial events and associated fields. | P0 | Not Started
S08 | Weapon Detection | Real-time AI identification of firearms and weapons | Display weapon detection event and associated camera/image details for review. | Run the agreed weapon detection analytics on the supplied camera stream. | Send weapon-related events to the customer-provided API as stated in S09. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and agreed test footage/scenarios. | Demonstrate detection and immediate field/command alert behavior in the POC scenario. | P0 | Not Started
S09 | Weapon Detection | Push all weapon events to customer-provided API in real time | Display event and delivery result where the POC UI provides it. | Prepare weapon event data and associated evidence references. | Push weapon events to customer-provided API in real time with image, video footprint/reference and camera details. | Backend/API Engineer | Customer API documentation, endpoint, credentials and required payload format. | Customer endpoint receives and validates weapon events and associated fields. | P0 | Not Started
S10 | Fire & Smoke Detection | Live video AI analytics for fire and smoke hazards | Display fire/smoke event and camera information where included in the POC monitoring interface. | Run fire and smoke detection analytics against the supplied live camera stream. | No separate event-to-customer-API requirement was explicitly stated for this use case in the email. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and agreed test footage/scenarios. | Demonstrate live fire/smoke analytics in agreed POC scenarios. | P0 | Not Started
S11 | Crowd & Object Analytics | People counting | Display people-counting output in the agreed monitoring view. | Run people-counting analytics on the supplied camera stream. | No separate event-to-customer-API requirement was explicitly stated for this use case in the email. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and agreed test scenario. | Demonstrate people counting in the agreed POC scenario. | P0 | Not Started
S12 | Crowd & Object Analytics | Crowd density and heat maps | Display crowd-density/heat-map output in the agreed monitoring view. | Run crowd-density analysis and generate heat-map output from the supplied camera stream. | No separate event-to-customer-API requirement was explicitly stated for this use case in the email. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and agreed test scenario. | Demonstrate crowd-density and heat-map output in the agreed POC scenario. | P0 | Not Started
S13 | Crowd & Object Analytics | Junction overcrowding management | Display the crowd/overcrowding output needed for the agreed POC demonstration. | Process the supplied stream for crowd density/overcrowding management as described in the email. | No separate event-to-customer-API requirement was explicitly stated for this use case in the email. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and agreed junction scenario. | Demonstrate the agreed junction-overcrowding scenario. | P0 | Not Started
S14 | Crowd & Object Analytics | Multi-class object / vehicle / person detection | Display detected classes and associated camera information in the agreed view. | Run multi-class detection for objects, vehicles and persons on the supplied camera stream. | No separate event-to-customer-API requirement was explicitly stated for this use case in the email. | AI/Computer Vision Engineer; Frontend Developer | Camera stream and agreed classes/scenarios. | Demonstrate detection of the agreed classes during the POC. | P0 | Not Started
S15 | Edge AI Software | Run all specified use cases on the supplied NVIDIA Jetson Orin Nano edge device | Display software/use-case status only if included in the agreed demonstration interface. | Deploy and configure the software for the email-listed use cases on the Jetson Orin Nano 16GB supplied by the customer; process camera streams on this device. | Support the API and ICCC flows listed in their respective tasks. | Edge AI Engineer; AI/Computer Vision Engineer; DevOps/Software Deployment Engineer | Jetson Orin Nano 16GB, suitable carrier, M.2/SSD storage, Linux/JetPack, industrial enclosure and power supply supplied by customer; confirm software-stack compatibility. | Demonstrate the agreed use cases processing camera streams on the supplied edge device. | P0 | Not Started
S16 | Software Installation / Configuration | Install, implement and configure the software for the agreed POC scope | Configure the software interface required for the listed use cases. | Install, implement and configure the video analytics software for the use cases listed in the email on the supplied hardware. | Configure only the customer API and ICCC integrations specified in this sheet. | Software Deployment Engineer; Edge AI Engineer; Integration Engineer | Hardware availability and access, camera streams, customer API/ICCC information. | Software is installed and configured for the agreed POC demonstration. | P0 | Not Started
S17 | ICCC Integration | Integrate with the existing ICCC platform for unified monitoring and analytics | Show agreed monitoring/events through the existing ICCC platform or its agreed integration view. | Provide the software-side integration needed to share the listed monitoring/analytics outputs with ICCC. | Implement the integration using the interface/protocol supplied or confirmed by the ICCC/customer team; do not assume an undocumented interface. | Integration Engineer; Backend/API Engineer | Existing ICCC integration documentation, access, endpoint/protocol and customer technical contact. | Demonstrate the agreed integration and validate event/monitoring visibility with the customer team. | P0 | Not Started
S18 | Live / Recorded Footage | Support ICCC monitoring and analytics on live streams and recorded footage | Demonstrate live-stream and recorded-footage access/analytics in the agreed platform workflow. | Process the available live streams and recorded footage using the specified software capabilities. | Use available ICCC/customer interfaces as supplied; no additional storage or platform features assumed. | Video Integration Engineer; AI/Computer Vision Engineer; Integration Engineer | Access to live streams, recorded footage and the existing ICCC platform. | Demonstrate the available live and recorded footage workflow agreed for the POC. | P0 | Not Started
S19 | Customisation | Consider only customisation requests related to the above use cases during POC | Implement only UI changes directly related to the listed use cases when requested and agreed. | Assess and implement only software customisation related to ANPR, FRS, weapon, fire/smoke, crowd/object analytics, edge processing or their stated integrations. | No unrelated modules or additional features included. | Project Manager; Relevant Software/AI Owner | Specific customer request and agreement that it is within the listed use cases. | Each agreed in-scope request is tracked and reviewed during the POC. | P1 | Not Started
S20 | POC Testing & Demonstration | Validate software behavior for the listed use cases during the live demonstration and 7-day ground POC | Present the listed use cases and relevant event details during the demonstration. | Run and tune only the listed use cases on the supplied edge hardware and camera streams; record observed detection behavior and performance during the POC. | Validate the API events explicitly required for ANPR, FRS and weapons, and validate the agreed ICCC integration. | POC Lead; QA/Test Engineer; AI/Integration Team | Agreed test scenarios, camera streams, customer API/ICCC access and demonstration schedule. | Demonstrate the email-listed capabilities and record results against criteria agreed with the customer. | P0 | Not Started